## Sheet1
Name	Week One	Week Two	Week Three	Week Four	Week Five	Week Six	Week Seven	Week Eight
Morlay Souare	Enviroment and Prop CA	Sky Box	Trailer Pre-Production	Infographic loading screen	Trailer Production/Editing	Iteration Based on Feedback	Iteration Based on Feedback	Testing/Polish
Tamara Hooijmans	Enviroment and Prop CA	Prop CA and UI Art	UI Art and Animations	UI Art Implmentation	3D Art Help	Iteration Based on Feedback	Iteration Based on Feedback	Testing/Polish
Ekin Kaya	Character CA	Block Out animations	3D Animations	3D Animations	Animation Unity Implemantation	Iteration Based on Feedback	Iteration Based on Feedback	Testing/Polish
Humam Abud Allah	Audio Research	Audio Production	Rigging	Audio Implementation	Trailer Production/Box Modelling	Iteration Based on Feedback	Iteration Based on Feedback	Testing/Polish
Tanya Schrijver	Character CA	Character Modelling	Character Modelling/German Translation	Character Modelling	Box Modelling	Iteration Based on Feedback	Iteration Based on Feedback	Testing/Polish
Rob O'Connor	Planning and 3D experimentation	Box Modelling	Rigging Shaders and Box Modelling	Shaders/Particles and Rigging	Box Modelling and Lighting + PP	Iteration Based on Feedback	Iteration Based on Feedback	Testing/Polish

Rick Oosthof	Game Design Doc	Senairo Writing and Economy	UI Scripting	Scripting	Testing/Scripting	Testing/Scripting	Testing/Scripting	Testing
Olivier de Haan	Topic and Audience Research	Senairo Writing and UI Design	Putting Scenairos to Unity	Testing/ Art Help	Testing/Art Help	Testing/Art Help	Testing/Art Help	Testing

Glyn Leine	GIT set-up and Earth Rotation PT	Sceaniro Tool				Testing/Polish	Testing/Polish	Testing/Polish

Project	Concepting and 1st PT	Art Production Begins, Game / Balance and 2nd PT	Rigging and Animation begin, Design / Implementation and 3rd PT	Wrapping Up of crucial art assets. / Design being iterated based on tests and 4th PT	All crucial Art in engine, Design being iterated based on tests and PT with all feature implemented	Iterating based on test results / and Polish	Iterating based on test results / and Polish	Iterating based on test results / and Polish